## Blad1
Sprint plan 1
context: Health Informatics
group: 3
User story | Task | Task assigned to | Estimated effort per task
As a user I want to read the txt file of the StatSensor® | select a file | jens | 2 hours
| convert to data | jens | 4 hours
| specify how and what columns are present | jens | 3 hours
| specify wich delimiter is used | jens | 2 hours
As a user I want to generate an output file. | specify the columns of the output file | paul | 2 hours
| specify wich delimiter is used | paul | 2 hours
| specify a location where the file is stored | paul | 2 hours
As a user I want to specify wich analysis I want to perform | specify the file where analysis is specified | louis + chris | 2 hours
| parse the operations | louis + chris | 5 hours
As a user I want to be able to perform a constraints analysis | specify what the constraint is | boudewijn | 4 hours
| execute the constraint | boudewijn | 4 hours
additional tasks:
product vision | chris + louis |  | 18 hours
language specification | all |  | 6 hours
software achitecture | all |  | 3 hours