## Blad1
Sprint plan 1
context | Health Informatics
group | 3
User story | Task | Task assigned to | Estimated effort per task
As a user I want to read the txt file of the StatSensor® | select a file | jens | 2 hours
| convert to data | jens | 4 hours
| specify how and what columns are present | jens | 3 hours
| specify wich delimiter is used | jens | 2 hours
As a user I want to generate an output file. | specify the columns of the output file | paul | 2 hours
| specify wich delimiter is used | paul | 2 hours
| specify a location where the file is stored | paul | 2 hours
As a user I want to specify wich analysis I want to perform | specify the file where analysis is specified | louis + chris | 2 hours
| parse the operations | louis + chris | 5 hours
As a user I want to be able to perform a constraints analysis | specify what the constraint is | boudewijn | 4 hours
| execute the constraint | boudewijn | 4 hours
additional tasks:
product vision | chris + louis |  | 18 hours
language specification | all |  | 6 hours
software achitecture | all |  | 3 hours
|  |  |  | product vision | Who is going to buy the product? Who is the target customer?
Which customer needs will the product address?
Which product attributes are crucial to satisfy the selected needs, and therefore to the succes of the product?