## Blad1
Sprint plan 2 | Monday, Tuesday no planned sessions. Thursday college.
context: Health Informatics
group: 3
User story | Task | Task assigned to | Estimated effort | Note
As a user I want to specify an xml file to describe the data files | Choose an xml file | Paul | 2 hours
| Filter the header from the file | Paul | 5 hours | Specified by RegEx
| Read the files from the xml file | Paul | 5 hours | specifying directories should be possible)
As a user I want to save a data model | Choose a data model to save | Chris | 2 hours
| Choose which columns to save and which delimiter to use | Chris | 2 hours
| Choose where to save the files | Chris | 4 hours | Check how SPSS reads files
As a user I want to apply a constraints analysis | Specify input data model | Boudewijn | 2 hours
| Apply constraints analysis | Boudewijn | 10 hours
additional tasks:
Product Vision | 15 hours | Louis
Product Planning | 15 hours | Jens
Discuss GUI with Wenxing | 0.5 hours | Paul & Jens
Build GUI template | 2 hours | Paul