## Blad1
Sprint reflection 1
context: Health Informatics
group: 3
User story | Task | Task assigned to | Estimated effort | Done by | actual effort | Done | Notes
As a user I want to read the txt file of the StatSensor® | select a file | jens | 2 hours |  |  | no
| convert to data | jens | 4 hours | jens | 5 hours | yes
| specify how and what columns are present | jens | 3 hours | boudewijn | 2.5 hours | no | user cannot choose it but the code contains the structure
| specify wich delimiter is used | jens | 2 hours |  |  | no
As a user I want to generate an output file. | specify the columns of the output file | paul | 2 hours |  |  | no
| specify wich delimiter is used | paul | 2 hours | chris | 2 hours | yes
| specify a location where the file is stored | paul | 2 hours |  |  | no | hardcoded
As a user I want to specify wich analysis I want to perform | specify the file where analysis is specified | louis + chris | 2 hours |  |  | no
| parse the operations | louis + chris | 5 hours |  |  | no
As a user I want to be able to perform a constraints analysis | specify what the constraint is | boudewijn | 4 hours |  |  | no
| execute the constraint | boudewijn | 4 hours |  |  | no
additional tasks:
product vision | chris + louis |  | 18 hours | louis + paul | 15 hours | yes
language specification | all |  | 6 hours | jens + boudewijn | 4 hours | yes | work in progress
software achitecture | all |  | 3 hours | jens + boudewijn | 4 hours | yes
Tasks not on spint plan
GUI design |  |  |  | all | 1 hour
basic GUI implementation |  |  |  | paul | 5 hours
setup git project |  |  |  | chris | 2 hours

## Blad2
Main problems
We overestimated ourselves and mainly overestimated the time available this week. | we had to scedule an emergency meeting where we discarded the sprint plan and assigned everyone smal tasks. This was done to make sure a working program was delivered at the end of the week.
testdata not available | we made do with the available information of the slides, we made an example of the StatSensor data ourselves to test our program.
waiting on eachother | As soon as possible we wanted a working version. In a branch usable code was created and other branches pulled from this branch instead of the master with pull requests and code review.
prepare for meeting | We did not know what to expect in the meeting wich lead to inefficient client time. For the next time we know what to expect.
too many last minute features | we started programming too late in the week and did not take the lectures and kingsday into account.
Adjustments for the next sprint plan
feature freeze after Wednesday | Make sure Wednesday we are ready for the meeting. This also leads to better code review
more frequent pull requests | For every new part, a new pull request must be created. This is to make sure that for example the right document is added.
more github communication | Use GitHub messages more frequently.
use github for Documents | For a clearer overview of our documents, we added our Tex files to the git repository.
preparation for meeting | For next meeting we prepare with questions for the user.